## Features
FarryOn — Features Built
# | Feature | Area | What it does | Status | Notes
1 | Multi-AI provider | Backend/App | Switch between Gemini, OpenAI, Grok, Mock per session | Done · verified | User picks in Settings
2 | Realtime voice + vision | Core | Live mic + camera streamed to AI, spoken replies | Done · verified | Gemini Live / Realtime
3 | Hands-free mic (auto VAD + anti-echo) | App | Just talk; mic muted while assistant speaks | Done · verified | Half-duplex
4 | Camera portrait/landscape + orientation | App | Switch + lock orientation | Done · verified
5 | Voice + pinch + preset camera zoom | App | Zoom by voice, pinch, or 1x/2x/4x chips with read-out | Done · verified
6 | Full-bleed camera + quality + rounded viewport | App | Professional camera frame | Done · verified
7 | Web search (Tavily + Google cross-check) | Backend | Both engines merged + cross-checked for accuracy | Done · live | Live scores limited
8 | Persist settings | App | Host/port/provider/keys saved across launches | Done · verified
9 | Notes & Tasks (voice + view screen) | Both | Create/recall; grouped-by-date list | Done · verified
10 | Voice task management | Both | Complete / edit / delete tasks by voice | Done · verified
11 | Reminders (local notifications) | App | Fire at exact time even asleep/locked | Done · verified | alarmClock mode
12 | Voice device-control | Both | Mute mic, camera on/off, rotate, end session | Done · verified
13 | Cloud deploy (Render) | Infra | Always-on backend at farryon-backend.onrender.com | Done · live | Blocks SMTP
14 | Reconnect button | App | Restart a session after it ends/drops | Done · verified
15 | Performance (long chats) | App | Transcript capped; video paused during TTS | Done · verified
16 | Location ("where am I") | Both | GPS + reverse-geocoded address via get_location | Done · not device-tested | Needs GPS test
17 | Chat history | App | Conversations saved; History tab | Done · verified
18 | Email — read (multi-provider IMAP) | Both | Gmail/Outlook/Yahoo/Hostinger/Custom; categories, full body, reply-suggest | Done · verified | Reading works on cloud
19 | Email — send (SMTP, confirm) | Both | Send from user's own mailbox after confirmation | Done · local only | Cloud blocks SMTP
20 | New logo + adaptive icon | App | Full-bleed winged-eye launcher + notification icon | Done · verified
21 | Professional chat UI | App | Polished bubbles, frosted panel, bigger chat | Done · verified
22 | Confirm-before-action | Backend | Asks before create/change/delete/send | Done · verified | All providers
23 | Landmark & Product Finder | Both | Identify place/product/object from camera | Done · verified | Gemini vision core
24 | Voice-driven finder (auto) | Both | "Take a photo & tell me" -> auto capture + classify | Done · verified | No tap needed
25 | Reply in user's language | Backend | Answers in the language the user speaks | Done · verified | All providers

## Bugs & Fixes
FarryOn — Bugs Found & Fixed
# | Issue | Severity | Root cause | Fix applied | Status
1 | Only 'thinking', no spoken response / double reply | High | Per-turn receive loop ended early; thoughts leaked | Multi-turn receive loop; skip thought parts | Fixed · verified
2 | Backend crash on boot (ALLOWED_ORIGINS) | High | pydantic parsed CSV env as JSON | Annotated NoDecode + CSV validator | Fixed · verified
3 | Mic went deaf + echo (manual VAD) | High | START_SENSITIVITY_LOW + full-duplex | Automatic VAD + client half-duplex | Fixed · verified
4 | Assistant heard its own voice (echo loop) | High | Mic re-opened before TTS tail finished | Mute margin 600->1200ms + drop user transcript during TTS | Fixed · verified
5 | Reminders never fired (release build) | Critical | R8 stripped Gson signatures -> receiver crash 'Missing type parameter' | Disable minify + proguard keep rules | Fixed · verified
6 | Reminders deferred (Doze/Battery Saver) | Critical | exactAllowWhileIdle throttled | AndroidScheduleMode.alarmClock | Fixed · verified
7 | Relative reminder ('in 2 min') dropped | Medium | clientTime frozen at connect -> resolved to past | Backend remind_in_seconds + fire-soon fallback | Fixed · verified
8 | APK install fail (version downgrade) | Low | Split vs single-ABI version codes | Uninstall + reinstall | Fixed
9 | Settings: can't enter password / Save hidden | High | Fixed Column not scrollable; keyboard pushed it off | Scrollable sheet + pinned Save bar + show/hide | Fixed · verified
10 | Launcher icon tiny (grey card in white squircle) | Medium | Legacy PNG, not adaptive | Full-bleed adaptive icon (bg + foreground) | Fixed · verified
11 | Web search wrong/made-up live scores | High | Trusted stale AI 'answer' / Google countdown | Cross-engine merge + pick authoritative, ignore countdowns | Fixed · verified
12 | Email category search 'couldn't sign in' | High | X-GM-RAW multi-word query sent unquoted | Quote the Gmail search query | Fixed · verified
13 | Email reply sent to WRONG address | Critical | Model guessed recipient | Parse exact from_email + confirm address aloud | Fixed · verified
14 | Email send 'timed out' on cloud | High | Render blocks outbound SMTP (587/465) | Works on local / SMTP-allowing host (Hostinger VPS/Fly.io) | Mitigated / documented
15 | Camera froze; had to force-close app | Critical | No lifecycle handling; controller dead after background | Release camera on background, re-open on resume | Fixed · verified
16 | Mic/assistant active in background during Finder | Medium | Live session not paused for finder sheet | Pause mic while Finder result open | Fixed · verified
17 | Top bar / settings gear cut during 'Connecting' | Medium | Full-width bar clipped by rounded viewport | Floating rounded bar + compact icons | Fixed · verified
18 | Scan: 'no camera frame yet' (camera on) | Medium | First frame ~1s after camera on/resume | grabFrame() waits ~2s for first frame | Fixed · verified
19 | Spoke English, transcript/reply in Hindi | High | Auto language; STT used Devanagari | Prompt: reply in user's spoken language (all providers) | Fixed · verified
20 | Landmark/product detail weak for local things | High | Google Vision recognises famous landmarks only | Gemini multimodal vision as core identifier | Fixed · verified
21 | Finder 404 on cloud | High | Finder code not deployed to Render | Deployed; set VISION_API_KEY in Render env | Fixed

## Summary
FarryOn — Status Report
Generated 2026-06-23 · branch claude/gallant-franklin-j6qzbx
Metric | Count
Total features
Features done & verified
Features pending device test / local-only
Total bugs logged
Bugs fixed & verified
Bugs mitigated / documented
Pending / Next
• Email SEND on cloud — Render blocks SMTP; deploy backend to Hostinger VPS / Fly.io for always-on send.
• Location — code done; needs on-device GPS test ("where am I").
• Finder on cloud — set VISION_API_KEY in Render dashboard.
• Web search live sports scores — general search can't guarantee; add a sports API if critical.
• Latest APK install + device-test of newest fixes (camera lifecycle, finder, language).